**6.7 Sample Registry Week Schedule**

CR Zero 2020 Connections Week Schedule

|  |  |  |
| --- | --- | --- |
| **Date and time** | **Locations** | **Teams** |
| Street outreach | |  |
| Tuesday, 30th August 9pm – 2am | * Queens Gardens * Croydon College Car Park * Whitgift Car Park, Whitgift Street * Front and back of Alders (CR9 1SB) * Fairfield Car Park * Derring Road Garages * **Hub: Alexandra House** | * 4 Team leader + 16 survey volunteers   1 Team leader + 4 Hub volunteers  (20 Volunteers)  (5 Staff) |
| Drop in morning |  |  |
| Wednesday 31st August (morning) 10am – 1pm | * Alexandra House | * 2 Team leader + 8 Survey volunteers * 4 Data Entry volunteers * 4 Hub volunteers * (16 volunteers) * (2 staff) |
| Street outreach | |  |
| Wednesday 31 August 9pm – 2am | * **NORTH of the Borough [TBC]** * **Hub: Alexandra House** | * 4 Team leader + 16 survey volunteers   1 Team leader + 4 Hub volunteers  (20 Volunteers)   * (5 Staff) |
| Street outreach | |  |
| Thursday 1 September 5am – 9am (Encampments) | TBC  **Hub: Alexandra House** | 3 Team leader + 12 Survey volunteers (TBC)   * 1 Team leader + 4 Hub volunteers * (16 volunteers) * (4 staff) |
| Drop in morning |  |  |
| Thursday 1 September 10am – 1pm | * **Hub: Alexandra House** * **Data inputting: MPH** | * 2 Team leader + 8 Survey volunteers * 4 Data Entry volunteers * 4 Hub volunteers * (16 volunteers) * (2 staff) |
| Data Day |  |  |
| Friday 2 September 10am – 4pm | * Alexandra House | * 1 Team leader + 8 Data Entry volunteers * (8 volunteers) * (1 staff) |
| Community feedback session/exhibition | |  |
| Saturday, 3rd September 12am – 1pm | TBC | TBC |

|  |  |
| --- | --- |
| Roles | Needed (if all do 1 shift) |
| Survey | 60 |
| Data | 16 |
| Hub | 20 |
| Team Leaders | 19 |
| Total Volunteers | 96 |
| Total Staff/Team Leaders | 19 |
| Total | 115 |