**6.7 Sample Registry Week Schedule**

CR Zero 2020 Connections Week Schedule

|  |  |  |
| --- | --- | --- |
| **Date and time** | **Locations** | **Teams** |
| Street outreach |  |
| Tuesday, 30th August 9pm – 2am  | * Queens Gardens
* Croydon College Car Park
* Whitgift Car Park, Whitgift Street
* Front and back of Alders (CR9 1SB)
* Fairfield Car Park
* Derring Road Garages
* **Hub: Alexandra House**
 | * 4 Team leader + 16 survey volunteers

1 Team leader + 4 Hub volunteers(20 Volunteers)(5 Staff) |
| Drop in morning |   |  |
| Wednesday 31st August (morning) 10am – 1pm  | * Alexandra House
 | * 2 Team leader + 8 Survey volunteers
* 4 Data Entry volunteers
* 4 Hub volunteers
* (16 volunteers)
* (2 staff)
 |
| Street outreach |  |
| Wednesday 31 August 9pm – 2am  | * **NORTH of the Borough [TBC]**
* **Hub: Alexandra House**
 | * 4 Team leader + 16 survey volunteers

1 Team leader + 4 Hub volunteers(20 Volunteers)* (5 Staff)
 |
| Street outreach |  |
| Thursday 1 September 5am – 9am (Encampments)  |  TBC**Hub: Alexandra House** | 3 Team leader + 12 Survey volunteers (TBC)* 1 Team leader + 4 Hub volunteers
* (16 volunteers)
* (4 staff)
 |
| Drop in morning |   |  |
| Thursday 1 September 10am – 1pm  | * **Hub: Alexandra House**
* **Data inputting: MPH**
 | * 2 Team leader + 8 Survey volunteers
* 4 Data Entry volunteers
* 4 Hub volunteers
* (16 volunteers)
* (2 staff)
 |
| Data Day |   |  |
| Friday 2 September 10am – 4pm | * Alexandra House
 | * 1 Team leader + 8 Data Entry volunteers
* (8 volunteers)
* (1 staff)
 |
| Community feedback session/exhibition |  |
| Saturday, 3rd September 12am – 1pm  |  TBC | TBC |

|  |  |
| --- | --- |
| Roles | Needed (if all do 1 shift) |
| Survey | 60 |
| Data | 16 |
| Hub | 20 |
| Team Leaders | 19 |
| Total Volunteers | 96 |
| Total Staff/Team Leaders | 19 |
| Total | 115 |